## 3 Months Out (Sept)
Task | Priority | Owner | Status | Start date | Deadline | Notes
Form GivingTuesday committee with clear roles | P0 |  | Not started
Set specific, measurable campaign goals
Determine participation approach (fundraising, volunteering, both)
Select ministry or project to benefit
Begin developing campaign theme and messaging
Audit online giving platform functionality
Create preliminary campaign budget
Begin collecting testimonials and impact stories
Schedule planning meetings with ministry leaders
Develop prayer strategy for the campaign

## 2 Months Out (Oct)
Task | Priority | Owner | Status | Start date | Deadline | Notes
Finalize campaign theme and messaging | P0 |  | Not started
Begin creating promotional materials
Develop comprehensive content calendar
Plan GivingTuesday worship service integration
Create campaign leanding page/website section
Identify key congregation ambassadors
Create resources for board members and leaders
Begin training campaign volunteers
Plan special events and prayer services
Prepare email templates using toolkit samples

## 1 Months Out (Nov)
Task | Priority | Owner | Status | Start date | Deadline | Notes
Finalize all promotional materials | P0 |  | Not started
Schedule all social media posts
Prepare press release using toolkit template
Test all online giving links and processes
Breif church staff on campaign details and roles
Begin pre-campaign awareness communications
Make initial weekend service announcements
Distribute promotional materials throughout church campus(es)
Activate prayer team for campaign
Prepare thank-you message templates by donor level
Send reminder communications to congregation
Conduce final technical systems check on your church management and giving solutions
Confirm all volunteer assignments and schedules
Prepare physical spaces for in-person elements
Schedule day-of email communications

## GivingTuesday Week
Task | Priority | Owner | Status | Start date | Deadline | Notes
Send final reminder email with clear instructions | P0 |  | Not started
Host pre-campaign prayer gathering
Conduct final online systems check
Prepare social media milestone graphics
Brief all volunteers on responsibilities
Launch campaign with inspiring message
Activate all scheduled communications
Monitor donation progress throughout the day
Share real-time updates and milestones
Engage with donors on social media
Send initial thank-you messages to early donors

## Post-Campaign Follow-Up
Task | Priority | Owner | Status | Start date | Deadline | Notes
Send personalized thank-you messages to all donors | P0 |  | Not started
Share preliminary results with congregation
Acknowledge volunteers and team members
Gather feedback while experience is fresh
Share final campaign results with congregation
Conduct team debrief meeting
Document lessons learned for future campaigns
Begin planning transparent fund implementation
Provide updates on funded projects
Share testimonials and impact stories
Analyze donor data for insights
Develop stewardship plan for new donors

## Committee and Contacts
Role | Name | Email | Phone Number | Primary Responsibilities | Meeting Availability

## Budget Tracker
Expense details | Category | Vendor/Source | Budget | Cost | Transaction date | Paid by | Notes
Promotional Materials
|  |  | 0 | 0

## Communications Calendar
Date | Communication Type | Audience | Message | Owner | Status | Engagement Metrics
| Email | Congregation | Message |  | Sent | 45% Open, 10% Click
| Social | Social Followers | Message |  | Posted | 120 Likes, 15 Shares